## Cover
CORRECTIVE & PREVENTIVE ACTION (CAPA)
Comprehensive Management of Nonconformities, Incidents & Root Causes — ISO 9001 / 14001 / 45001
Organization Profile
Organization | [Enter organization]
Site / Location | [Enter site]
Management Representative | [Name]
Reporting Period | [YYYY-MM-DD to YYYY-MM-DD]
Standards in Scope | ISO 9001 · ISO 14001 · ISO 45001
Document Owner | Quality, HSE & Compliance
Revision | Rev 1.0 — June 2026
Workbook Contents
1. Dashboard | Live KPIs, status, source mix, ISO clause heatmap
2. NC & Incident Log | Master register of nonconformities, incidents, audit findings, complaints
3. Root Cause Analysis | 5-Why, Fishbone (6M), Pareto linkage per CAPA
4. CAPA Register | Corrective & preventive actions with owners, dates, verification
5. Effectiveness Review | Post-implementation verification & closure approval
6. Recurrence Tracker | Repeat NC/incident detection by category & clause
7. ISO Clause Mapping | Linkage to 9001/14001/45001 clauses 4–10
8. Cost of Poor Quality | Direct, indirect, and prevention cost capture
9. Lessons Learned | Knowledge capture for institutional learning
10. Reference Guide | Procedure, definitions, RACI, escalation matrix
Confidential — for internal management system use only.

## Dashboard
CAPA MANAGEMENT DASHBOARD
Live indicators from the NC Log and CAPA Register.
| Total NCs Logged |  | Open CAPAs |  | Overdue | Closed
| 5 |  | 4 |  | 0 | 0
| Effective CAPAs |  | Recurrence Items |  | High Risk NCs (≥15) | Total COPQ (₦)
| 2 |  | 1 |  | 1 | 7340000
Status Breakdown
| Status | Count |  | Source | Count | Standard | Count
| Open | 2 |  | Internal Audit | 2 | ISO 9001 | 2
| In Progress | 2 |  | External Audit | 0 | ISO 14001 | 2
| Pending Verification | 1 |  | Incident | 1 | ISO 45001 | 1
| Closed | 0 |  | Near Miss | 0 | Integrated | 0
| Overdue | 0 |  | Customer Complaint | 1
| Cancelled | 0 |  | Inspection | 1

## NC & Incident Log
NC & INCIDENT LOG — Master Register
Capture every nonconformity, incident, audit finding, customer complaint, or near miss.
NC ID | Date Raised | Source | Type | Standard | Clause | Site/Process | Description | Immediate Containment | Severity (1-5) | Likelihood (1-5) | Risk Score | Reported By | Assigned Owner | Target Closure | Status | Linked CAPA ID | Recurrence?
NC-001 | 2026-05-12 | Internal Audit | Major NC | ISO 9001 | 8.5 | Production Line A | Calibration of torque wrench expired 45 days prior to use on critical assembly. | Quarantined batch; recalibrated tool. | 4 | 4 | 16 | J. Adeyemi | O. Bello | 2026-06-30 | In Progress | CAPA-001 | No
NC-002 | 2026-05-18 | Incident | Minor NC | ISO 45001 | 8.1.2 | Warehouse | Forklift near miss with pedestrian at blind corner. | Cordoned area; toolbox talk issued. | 3 | 4 | 12 | S. Musa | T. Okafor | 2026-06-15 | Open | CAPA-002 | Yes
NC-003 | 2026-05-22 | Customer Complaint | Major NC | ISO 9001 | 8.7 | Dispatch | Wrong product variant shipped to key account. | Recalled shipment; replacement dispatched. | 4 | 3 | 12 | Customer Care | C. Eze | 2026-06-10 | In Progress | CAPA-003 | No
NC-004 | 2026-05-28 | Inspection | Observation | ISO 14001 | 8.1 | Tank Farm | Minor hydrocarbon sheen in containment bund. | Spill kit deployed; bund cleaned. | 2 | 3 | 6 | HSE Team | R. Yusuf | 2026-06-20 | Open | CAPA-004 | No
NC-005 | 2026-06-01 | Internal Audit | Minor NC | ISO 14001 | 6.1.2 | Workshop | Aspects register not updated after new solvent introduction. | Aspect assessed and added. | 2 | 2 | 4 | EMS Coord. | K. Ibrahim | 2026-07-15 | Open | CAPA-005 | No
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Root Cause Analysis
ROOT CAUSE ANALYSIS — 5-Why & Fishbone (6M)
Complete per CAPA. Use 5-Why for systemic drill-down; Fishbone for category-based exploration.
| CAPA ID | [e.g. CAPA-001] | Problem Statement | [Describe the observed problem with facts, location, magnitude]
5-WHY ANALYSIS — Drill to System-Level Cause
| # | Question |  | Answer / Evidence
| Why 1 | Why did the problem occur?
| Why 2 | Why did that happen?
| Why 3 | Why did that happen?
| Why 4 | Why did that happen?
| Why 5 | Root system cause?
ROOT CAUSE
FISHBONE (ISHIKAWA) — 6M Categorical Analysis
| Category | Probing Prompts |  | Contributing Causes Identified | Most Likely? (Y/N)
| Man (People) | Skills, training, fatigue, communication, awareness
| Machine (Equipment) | Reliability, calibration, maintenance, capability
| Method (Process) | Procedures, instructions, controls, workflow
| Material | Quality, specification, supplier, storage
| Measurement | Calibration, criteria, inspection method, data integrity
| Mother Nature (Environment) | Weather, layout, lighting, housekeeping, workplace conditions
ROOT CAUSE CONFIRMATION & TECHNIQUE
Confirmed Root Cause
Technique(s) Used
Analysis Team

## CAPA Register
CORRECTIVE & PREVENTIVE ACTION REGISTER
Every CAPA must address (a) immediate correction, (b) root cause elimination, (c) recurrence prevention, and (d) effectiveness verification.
CAPA ID | Linked NC ID | Date Opened | Action Type | Standard | Clause | Root Cause Summary | Corrective Action (Fix) | Preventive Action (Prevent Recurrence) | Action Owner | Resources/Cost (₦) | Target Date | Actual Closure | % Complete | Status | Verification Method | Verified By | Effective? (Y/N)
CAPA-001 | NC-001 | 2026-05-13 | Corrective + Preventive | ISO 9001 | 8.5 | Calibration schedule not integrated with PM system; manual reminders missed. | Recalibrate tool; verify last 30 assemblies for torque compliance. | Integrate calibration register into CMMS with auto-alerts 30/14/7 days before due. Train tool custodians. | O. Bello | 450000 | 2026-06-30 |  | 60 | In Progress | Audit re-check + CMMS log review | QA Manager
CAPA-002 | NC-002 | 2026-05-19 | Preventive | ISO 45001 | 8.1.2 | Inadequate pedestrian/vehicle segregation at warehouse blind corner. | Install convex mirror and audible reverse alarms. | Redesign traffic management plan; add painted walkways, barriers, and proximity sensors. Refresher training for all forklift operators. | T. Okafor | 1200000 | 2026-06-15 |  | 40 | In Progress | Re-inspection + incident trend (90d) | HSE Manager
CAPA-003 | NC-003 | 2026-05-23 | Corrective + Preventive | ISO 9001 | 8.7 | Dispatch picking relied on memory; no scan verification at pack-out. | Replace shipment; issue customer apology. | Implement barcode scan-to-pack with mandatory match before label print. Update dispatch SOP and retrain. | C. Eze | 2800000 | 2026-06-10 |  | 75 | Pending Verification | Customer complaints trend + dispatch error rate | Operations Director
CAPA-004 | NC-004 | 2026-05-29 | Corrective | ISO 14001 | 8.1 | Drum decanting performed without secondary containment tray. | Clean bund; review aspect register. | Procure decant trays at all draw-off points; update SOP; spill drill quarterly. | R. Yusuf | 350000 | 2026-06-20 |  | 25 | Open | Site inspection + spill log | HSE Coordinator
CAPA-005 | NC-005 | 2026-06-02 | Preventive | ISO 14001 | 6.1.2 | No trigger to re-evaluate aspects when new chemicals introduced. | Add solvent to aspect/impact register. | Embed aspect re-evaluation step into Management-of-Change workflow; train MOC owners. | K. Ibrahim | 150000 | 2026-07-15 |  | 10 | Open | MOC log audit | EMS Coordinator

## Effectiveness Review
CAPA EFFECTIVENESS VERIFICATION & CLOSURE
No CAPA is closed without documented evidence that the action eliminated the cause AND prevented recurrence.
CAPA ID | Verification Date | Reviewer | Method Applied | Sample/Evidence | Recurrence in Period? (Y/N) | KPI Before | KPI After | Improvement % | Effectiveness Rating | Conclusion | Closure Approved By | Closure Date
CAPA-001 | 2026-08-15 | Internal Auditor | CMMS log audit + 30-tool spot check | 100% calibration alerts triggered; 0 missed in 60d | No | 6 | 0 | 100% | Effective | Recurrence eliminated; integrate into CMMS standard | QA Manager | 2026-08-20
CAPA-003 | 2026-09-01 | Operations | Dispatch error analytics dashboard | Scan-to-pack live; 1,420 shipments without error | No | 4 | 0 | 100% | Effective | Process change embedded | Ops Director | 2026-09-05

## Recurrence Tracker
RECURRENCE TRACKER — Systemic Weakness Detection
Repeat occurrences of the same failure mode indicate weak root-cause analysis or ineffective CAPA. Escalate any item with ≥3 occurrences.
Failure Mode / Category | Standard | Clause | Occurrences (12 mo) | Open CAPAs | Last Occurrence | Trend | Systemic Risk | Action
Calibration / measurement drift | ISO 9001 | 7.1.5 | 4 | 1 | 2026-05-12 | Increasing | High | Move to systemic CAPA; CMMS integration
Pedestrian-vehicle near miss | ISO 45001 | 8.1.2 | 3 | 1 | 2026-05-18 | Stable | High | Redesign traffic plan; barriers
Dispatch wrong-variant | ISO 9001 | 8.7 | 2 | 1 | 2026-05-22 | Decreasing | Medium | Monitor post scan-to-pack rollout
Minor hydrocarbon spill in bund | ISO 14001 | 8.2 | 3 | 1 | 2026-05-28 | Stable | Medium | Decant trays site-wide; quarterly drill
Aspect register not updated on MOC | ISO 14001 | 6.1.2 | 2 | 1 | 2026-06-01 | New | Medium | Embed MOC trigger
PPE compliance lapse | ISO 45001 | 8.1 | 5 | 0 | 2026-04-22 | Stable | High | Behavioural safety programme
Document version control failure | ISO 9001 | 7.5.3 | 2 | 0 | 2026-03-15 | Decreasing | Low | Monitor
PARETO — Vital Few Categories Driving 80% of Issues
Category | Count | Cumulative %
PPE compliance lapse | 5 | 23.81%
Calibration / measurement drift | 4 | 42.86%
Pedestrian-vehicle near miss | 3 | 57.14%
Minor hydrocarbon spill in bund | 3 | 71.43%
Dispatch wrong-variant | 2 | 80.95%
Aspect register not updated on MOC | 2 | 90.48%
Document version control failure | 2 | 100%

## ISO Clause Mapping
CAPA — ISO CLAUSE MAPPING (9001 / 14001 / 45001)
Every NC/incident is anchored to a clause. Use to demonstrate coverage in audits and management review.
Clause | Title | ISO 9001 | ISO 14001 | ISO 45001 | Typical NC/Incident Triggers | CAPA Linkage
4.1 | Context of the organization | ✓ | ✓ | ✓ | Strategic shifts unaddressed; missed external/internal issue | CAPA reviews update context
4.2 | Needs of interested parties | ✓ | ✓ | ✓ | Stakeholder requirement missed | Update register; communication CAPA
5.1 | Leadership & commitment | ✓ | ✓ | ✓ | Lack of visible leadership in incident response | Leadership engagement plan
6.1 | Risks & opportunities / Aspects / Hazards | ✓ | ✓ | ✓ | Unidentified risk → incident | Risk re-assessment CAPA
6.1.2 | Environmental aspects |  | ✓ |  | Aspect not evaluated on change | MOC integration
6.1.2 | Hazard identification |  |  | ✓ | Hazard missed in JSA | JSA refresh; training
7.1.5 | Monitoring & measurement resources | ✓ | ✓ | ✓ | Calibration / measurement drift | Calibration system CAPA
7.2 | Competence | ✓ | ✓ | ✓ | Untrained personnel cause NC | Competency CAPA
7.5 | Documented information | ✓ | ✓ | ✓ | Wrong document version in use | Document control CAPA
8.1 | Operational planning & control | ✓ | ✓ | ✓ | Process executed outside controls | Process control CAPA
8.2 | Emergency preparedness |  | ✓ | ✓ | Spill / fire / evacuation gaps | Drill & response CAPA
8.4 | External providers | ✓ |  |  | Supplier non-conformance | Supplier CAPA
8.5 | Production / service provision | ✓ |  |  | Process deviation | SOP & control CAPA
8.7 | Nonconforming outputs | ✓ |  |  | Wrong product released | Containment & recurrence CAPA
9.1 | Monitoring & evaluation | ✓ | ✓ | ✓ | KPI miss / data integrity | KPI review CAPA
9.1.2 | Customer satisfaction | ✓ |  |  | Repeat complaint | Customer experience CAPA
9.1.2 | Evaluation of compliance |  | ✓ | ✓ | Regulatory breach | Compliance CAPA
9.2 | Internal audit | ✓ | ✓ | ✓ | Audit programme gap | Programme revision
9.3 | Management review | ✓ | ✓ | ✓ | Action not assigned/tracked | MR action register
10.1 | Improvement — general | ✓ | ✓ | ✓ | No improvement evidence | Improvement portfolio
10.2 | NC & corrective action | ✓ | ✓ | ✓ | Recurring NCs / weak RCA | CAPA process upgrade
10.3 | Continual improvement | ✓ | ✓ | ✓ | Plateau in KPIs | Strategic improvement CAPA

## Cost of Poor Quality
COST OF POOR QUALITY (COPQ) — Financial Impact of NCs & Incidents
Quantify true cost: internal/external failure, appraisal (detection), and prevention investment.
NC/CAPA ID | Category | Description | Internal Failure (₦) | External Failure (₦) | Appraisal (₦) | Prevention (₦) | Total (₦)
CAPA-001 | Internal failure | Rework + production halt for tool recalibration | 380000 | 0 | 40000 | 450000 | 870000
CAPA-002 | Prevention | Traffic management redesign and training | 0 | 0 | 0 | 1200000 | 1200000
CAPA-003 | External failure | Recall, replacement shipment, customer credit | 0 | 1850000 | 0 | 2800000 | 4650000
CAPA-004 | Internal failure | Spill clean-up materials and labour | 120000 | 0 | 0 | 350000 | 470000
CAPA-005 | Prevention | MOC integration training and documentation | 0 | 0 | 0 | 150000 | 150000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL |  |  | 500000 | 1850000 | 40000 | 4950000 | 7340000

## Lessons Learned
LESSONS LEARNED — Institutional Knowledge Capture
Convert each closed CAPA into shared organizational learning.
CAPA ID | Date | Theme | What Happened | What We Learned | Knowledge Transfer Action | Audience | Status
CAPA-001 | 2026-08-20 | Asset reliability | Calibration drift caused product release with out-of-spec torque. | Manual calibration tracking fails at scale; integrate with CMMS and trigger alerts. | Add to onboarding for all QA & maintenance staff; case study briefing. | QA, Maintenance, Production | Published
CAPA-003 | 2026-09-05 | Process control | Memory-based dispatch led to wrong-variant shipment to top customer. | Engineer mistakes out via mandatory scan-verification before label print. | Toolbox brief; updated SOP cascade; cross-site rollout. | Logistics, Customer Care | Published

## Reference Guide
CAPA PROCEDURE — REFERENCE GUIDE
Process flow, definitions, RACI and escalation matrix
Process Flow (10 Steps)
| Step 1 — Detect & Report | Anyone identifies an NC, incident, near miss, complaint, or audit finding and raises it in the NC Log within 24 hours.
| Step 2 — Contain | Immediate correction to protect customer, environment, and people. Document containment in NC Log column 'Immediate Containment'.
| Step 3 — Classify & Assess Risk | Classify severity & likelihood; calculate risk score (S×L). Major NC = formal CAPA mandatory.
| Step 4 — Investigate (RCA) | Use 5-Why for systemic causes; Fishbone (6M) for categorical exploration; Pareto for trend significance. Confirm root cause with evidence.
| Step 5 — Plan CAPA | Define corrective (fix) + preventive (eliminate recurrence) actions, owner, target date, resources, and verification method.
| Step 6 — Implement | Execute actions; track % complete and status; update CAPA Register weekly.
| Step 7 — Verify Effectiveness | Wait one full cycle (typically 60–90 days); verify with audit, KPI review, sample re-inspection. Record on Effectiveness Review sheet.
| Step 8 — Close | Closure approved by Management Representative only if 'Effective'. Otherwise re-open and escalate.
| Step 9 — Learn & Share | Convert outcomes into Lessons Learned; update procedures, training, and risk register.
| Step 10 — Review | Report CAPA KPIs at Management Review (clause 9.3); track recurrence and COPQ trends.
Key Definitions
| Correction | Action to eliminate a detected nonconformity (the symptom).
| Corrective Action | Action to eliminate the CAUSE of a nonconformity to prevent recurrence.
| Preventive Action | Action to eliminate the cause of a POTENTIAL nonconformity (risk-based thinking).
| Nonconformity (NC) | Non-fulfilment of a requirement.
| Incident | Occurrence arising from work that could/did result in injury, ill health or environmental harm.
| Near Miss | Incident with no injury, harm or loss — but with potential.
| Root Cause | Initiating cause of a causal chain that, if removed, prevents recurrence.
| Effectiveness | Extent to which planned activities are realized and planned results achieved.
RACI (typical)
| Originator | Reports NC/incident, supports investigation
| Action Owner | Responsible (R) — executes CAPA
| Process Owner | Accountable (A) — owns the outcome
| Management Rep / QHSE Manager | Consulted (C) — approves closure
| Top Management | Informed (I) — reviews KPIs at Management Review
Escalation Matrix
| Risk Score 1–6 (Low) | Action Owner closes within 30 days
| Risk Score 8–12 (Medium) | Process Owner reviews weekly; close within 60 days
| Risk Score 15–20 (High) | Management Rep reviews; close within 30 days; report at next MR
| Risk Score 25 (Critical) / Major NC / Recurring | Escalate to Top Management within 24 hours; formal investigation; root cause review board